## Release Plan
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2016-09-07 | 7 | 2016-09-13 | 0 | Planned |  | Requirement & Design (DB, UI, UX)
2 | 2016-09-14 | 7 | 2016-09-20 | 0 | Planned
3 | 2016-09-21 | 7 | 2016-09-27 | 0 | Planned |  | Prototype
4 | 2016-09-28 | 7 | 2016-10-04 | 0 | Planned
5 | 2016-10-05 | 7 | 2016-10-11 | 0 | Planned
6 | 2016-10-12 | 7 | 2016-10-18 | 0 | Planned |  | Basic Feature
7 | 2016-10-19 | 7 | 2016-10-25 | 0 | Planned
8 | 2016-10-26 | 7 | 2016-11-01 | 0 | Planned |  | Advanced Feature
9 | 2016-11-02 | 7 | 2016-11-08 | 0 | Planned |  | Report 2 SPM
10 | 2016-11-09 | 7 | 2016-11-15 | 0 | Planned |  | Report 3 SRS
11 | 2016-11-16 | 7 | 2016-11-22 | 0 | Planned |  | Report 4 SDD
12 | 2016-11-23 | 7 | 2016-11-29 | 0 | Planned |  | Report 5
13 | 2016-11-30 | 7 | 2016-12-06 | 0 | Planned |  | Report 6 User Manual
|  |  | Unallocated stories | 0
Formulas:
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")
Note on H9: phuctran93: Teacher and Learner can conduct a lesson meeting.
Note on H11: phuctran93: - Rank Teacher - Learner Chat - Payment - Remind Meeting

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
100 | Authentication | Planned
101 | Login | Planned |  | 1
102 | Register | Planned |  | 1
200 | Teacher | Planned |  | 3
201 | Create Course | Planned |  | 3
202 | View Course | Planned
203 | Edit Course | Planned
204 | Delete Course | Planned
205 | Open Course | Planned
206 | Close Course | Planned
207 | View Enrolled Learner | Planned
208 | View Learner Rank | Planned
209 | Create Time Frame | Planned |  | 3
210 | View Time Frame | Planned
211 | Edit Time Frame | Planned
212 | Delete Time Frame | Planned
213 | Manage Chapter | Planned |  | 3
214 | Manage Lesson | Planned |  | 3
215 | Withdraw Money | Planned
300 | Learner | Planned |  | 3
301 | Search Teacher | Planned |  | 3
302 | Search Course | Planned |  | 3
303 | View Enrolled Course | Planned
304 | View Course Detail | Planned
305 | Enroll Course | Planned
306 | Vote Course | Planned
307 | View Teacher's Time Frame | Planned
308 | Follow Teacher | Planned
309 | View Course Report | Planned
310 | Deposit Money | Planned
400 | Authenticated User | Planned |  | 5
401 | View Registered Slot | Planned
402 | Cancel Registration | Planned
403 | Login to Meeting | Planned
404 | Cancel Meeting | Planned
405 | View Profile | Planned
406 | Edit Profile | Planned
407 | Use Support Tool | Planned
500 | System | Planned |  | 6
501 | Remind User for a Meeting | Planned
502 | Notify New Course | Planned
503 | Rank Teacher | Planned
Sort Product Backlog
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 60 |  | Sprint count | 3
Count trend from last |  |  | 3 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 30 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 |  |  | 25 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 25 |  | Trend count | 4 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 25 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 25 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 25 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 2
Original estimate - Avg |  |  | 2
Original estimate - Max |  |  | 4 |  | Standard Dev. | 2.8284
3 |  |  | 3
Realized average |  |  | 3 |  | LastPlanned | 10
Average last 8 |  |  | 3 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 3
Trend |  |  | 3
Realized + St. Dev |  |  | 3
Realized - St. Dev |  |  | 3
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 60 | 23 | 23 | 60 | 60 | 60 | 0 | 0 | 60 | 60.6667 | 60.6667 | 0 | 25 | 25 | 25
2 | 37 | 29 | 27 | 60 | 37 | 37 | 0 | 0 | 37 | 35.6667 | 35.6667 | 0 | 25 | 25 | 25
3 | 10 | 60 |  | 60 | 10 | 10 | 0 | 0 | 10 | 10.6667 | 10.6667 | 0 | 25 | 25 | 25
4 |  | 28 | [7 empty] | 0 | 0 | 0 | 25 | 25 | 25
5 |  | 28 | [7 empty] | 0 |  | 0 | 25 | 25 | 25
6 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
7 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
8 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
9 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
10 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
11 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
12 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
13 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
14 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
15 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
16 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
17 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
18 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
19 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
20 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
21 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
22 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
23 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
24 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
2016-09-07
2016-09-13
Sprint implementation days | 7 |  |  | Effort (hour) |  | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 36 | 20 | 4 | 5 | 4 | 2 | 1
Task rows | 10 | Done days | 5 |  |  | 36 | 30.8571 | 25.7143 | 20.5714 | 15.4286 | 10.2857 | 5.1429
Warning! These are necessary |  | Trend |  |  |  | 5 | 4.1 | 3.2 | 2.3 | 1.4 | 0.5
template rows |  | Trend Days | 5 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | Remain | 5 1: 1; 4.1 2: 2; 3.2 3: 3; 2.3 4: 4; 1.4 5: 5; 0.5 6: 6; 0.5 7: 7
Design ERD |  | HungVK | Planned | 2 | 0 | 4.1 2: 2
Design Overview Usecase |  | DuyNC | Planned | 1 | 0 | bar: 4.1 2
Design Physical database |  | HungVK | Planned | 2 | 0 | 3.2 3: 2
Design Class diagram |  | HungVK | Planned | 2 | 0 | 3.2 3: 2
Report 1: Introduction |  | PhucTQ | Planned | 5 | 2 | 2.3 4: 2; 1.4 5: 1
UI: Login Page |  | ThanhNP | Planned | 3 | 3
UI: Register Page |  | ThanhNP | Planned | 3 | 3
UI: Home Page |  | ThanhNP | Planned | 5 | 5
UI: Search Page |  | ThanhNP | Planned | 8 | 4 | 5 1: 2; 4.1 2: 2
UI: Search Result Page |  | ThanhNP | Planned | 5 | 3 | 5 1: 2
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
2
2016-09-14
2016-09-20
Sprint implementation days | 7 |  |  | Effort (hour) |  | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 12 | 0 | 0 | 3 | 4 | 2 | 1
Task rows | 5 | Done days | 4 |  |  | 12 | 10.2857 | 8.5714 | 6.8571 | 5.1429 | 3.4286 | 1.7143
Warning! These are necessary |  | Trend |  |  |  | 1.2 | 1.9 | 2.6 | 3.3 | 4 | 4.7 | 5.4 | 6.1 | 6.8 | 7.5 | 8.2 | 8.9 | 9.6 | 10.3 | 11 | 11.7 | 12.4 | 13.1 | 13.8 | 14.5 | 15.2 | 15.9 | 16.6 | 17.3 | 18
template rows |  | Trend Days | 4 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | Remain | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Bom: Register API | 2 | PhucTQ | Done | 2 | 0 | 2: 2
Mockup: Register | 2 | PhucTQ | Done | 1 | 0 | bar: 2
Bom: Login API | 1 | PhucTQ | Done | 2 | 0 | 3: 2
App: Login in | 1 | PhucTQ | Done | 2 | 0 | 3: 2
App: Login using Facebook | 1 | DuyNC | Done | 5 | 0 | 4: 2; 5: 1
Bom: Create Course API | 7 | PhucTQ | Done | 3 | 0
Bom: Teacher View Course API | 8 | PhucTQ | Done | 3 | 0
Bom: Create TimeFrame API | 3 |  | Done | 5 | 0
Bom: Teacher View TimeFrame API | 4 |  | Done | 3 | 0 | 1: 2; 2: 1
App: Create Course | 7 | PhucTQ | Done | 5 | 0 | 2: 2; 3: 2; 4: 1
App: Teacher View Course | 8 | PhucTQ | Done | 5 | 0 | 2: 2; 3: 2; 4: 1
App: Create TimeFrame | 3 |  | Done | 3 | 0 | 1: 2; 2: 1
App: Teacher View TimeFrame | 4 |  | Done | 3 | 0 | 4: 2; 5: 1
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
3
2016-09-21
2016-09-27
Sprint implementation days | 7 |  |  | Effort (hour) |  | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 60 | 34 | 10 | 8 | 6 | 6
Task rows | 21 | Done days | 4 |  |  | 60 | 51.4286 | 42.8571 | 34.2857 | 25.7143 | 17.1429 | 8.5714
Warning! These are necessary |  | Trend |  |  |  | 9.6 | 8.2 | 6.8 | 5.4 | 4 | 2.6 | 1.2
template rows |  | Trend Days | 4 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | Remain | 9.6 1: 1; 8.2 2: 2; 6.8 3: 3; 5.4 4: 4; 4 5: 5; 2.6 6: 6; 1.2 7: 7
Doc: Design Use-case Diagram |  | PhucTQ | Done | 4 | 0 | 9.6 1: 2; 8.2 2: 2
Doc: Design Conceptual Data Model |  | PhucTQ | Done | 8 | 0 | 9.6 1: 4; 8.2 2: 3; 6.8 3: 1
Doc: Design Logical Data Model |  | PhucTQ | Done | 8 | 0 | 9.6 1: 4; 8.2 2: 3; 6.8 3: 1
Doc: Design Physical Data Model |  | DuyNC | Ongoing | 4 | 4 | 9.6 1: 0; 8.2 2: 0
UI: Login |  | PhucTQ | Done | 2 | 0 | 5.4 4: 2
UI: Register |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Course |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Chapter |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Lesson |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Time Frame |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Time Slot |  | PhucTQ | Planned | 2 | 2
UI: Learner Search Teacher |  | DuyNC | Ongoing | 2 | 2
UI: Learner Search Course |  | DuyNC | Ongoing | 2 | 2
UI: Leaner View Teacher Details |  | DuyNC | Planned | 2 | 2
UI: Leaner View Course Details |  | DuyNC | Planned | 2 | 2
UI: Leaner Follow Teacher |  | DuyNC | Planned | 2 | 2
UI: Leaner Enroll Course |  | DuyNC | Planned | 2 | 2
UI: Leaner Register Time Slot |  | DuyNC | Planned | 2 | 2
UI: Teacher View Upcomming Meeting |  | DuyNC | Planned | 2 | 2
UI: Leaner View Upcomming Meeting |  | DuyNC | Planned | 2 | 2
API: Deploy Bom to OpenShift |  | PhucTQ | Cancelled | 4 | 0 | 6.8 3: 4; 5.4 4: 4
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp4
4
07/06/2016 - 14/06/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 100 | 15 | 20 | 19 | 15 | 7 | 9 | 14
Task rows | 27 | Done days | 7 |  | 100 | 85.7143 | 71.4286 | 57.1429 | 42.8571 | 28.5714 | 14.2857
Warning! These are necessary |  | Trend |  |  | 19.2 | 17.6 | 16 | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
UI: P231 |  | NghiaDH | Done | 3 | 1: 2; 2: 1
UI: P232 |  | NghiaDH | Done | 2 | 2: 2
UI: P233 |  | NghiaDH | Done | 3 | 3: 3
UI: P241 |  | NghiaDH | Done | 2 | 1: 2
UI: P242 |  | NghiaDH | Done | 2 | 2: 2
UI: A441 |  | NghiaDH | Done | 1 | bar: 1
UI: A451 |  | ThanhLD | Done | 2 | 1: 2
UI: A471 |  | ThanhLD | Done | 2 | 2: 2
UI: A472 |  | ThanhLD | Done | 2 | 3: 2
UI: A481 |  | ThanhLD | Done | 3 | 3: 2; 4: 1
UI: A482 |  | ThanhLD | Done | 2 | 4: 2
Integrate current UI of Parent with API |  | NghiaDH | Ongoing | 6 | 4: 3; 5: 2; 6: 1
Integrate current UI of Admin with API |  | ThanhLD | Done | 8 | 3: 4; 4: 3; 5: 1
API: Immunization List (Child/ standard) |  | NghiaDH | Done | 5 | 1: 2; 2: 2; 3: 1
API: Immunization Detail (Child/ standard) |  | NghiaDH | Done | 3 | 2: 2; 3: 1
API: Create Nutrition suggestion for child |  | ThanhLD | Done | 5 | 1: 3; 2: 2
API: Check attendence |  | ThanhLD | Done | 4 | 2: 2; 3: 2
API: Check child health |  | ThanhLD | Done | 5 | 4: 3; 5: 1
API: List teaching schedule |  | AnhND | Done | 3 | 1: 3
API: create teaching schedule |  | AnhND | Done | 2 | 2: 2
API: Post CRUD |  | ThanhLD | Done | 3 | 3: 2; 4: 1
Research: Stored video when streaming. |  | ThanhLD | Done | 5 | 2: 1; 3: 1; 4: 1; 5: 2
Research: Stored video when streaming. |  | NghiaDH | Done | 5 | 2: 2; 3: 1; 4: 1; 5: 1
System integration. Preparing Alpha version for releasing. |  | ThanhLD | Ongoing | 15 | 6: 8; 7: 7
Guest and Parent function test |  | NghiaDH | Ongoing | 3 | 7: 3
Admin and Teacher functions test |  | AnhND | Ongoing | 3 | 7: 3
System test. |  | ThanhLD | Ongoing | 1 | bar: 7
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Task Slips
Story ID: | 1 | Story: | This is a sample story
Task: | Example task
#REF!
Initial Estimate | 5 | Work Done |  | Work Left
Story ID: | 1 | Story: | This is a sample story
Task: | Example task 2
Responsible Person: HungVK
Initial Estimate | 7 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | Example task 3
Responsible Person: DuyNC
Initial Estimate | 12 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | <Delete these example lines>
Responsible Person: HungVK
Initial Estimate | 9 | Work Done |  | Work Left