## Release Plan
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2016-05-17 | 7 | 2016-05-23 | 0 | Planned |  | Requirement & Design (DB, UI, UX)
2 | 2016-05-24 | 7 | 2016-05-30 | 0 | Planned
3 | 2016-05-31 | 7 | 2016-06-06 | 0 | Planned
4 | 2016-06-07 | 7 | 2016-06-13 | 0 | Planned
5 | 2016-06-14 | 7 | 2016-06-20 | 0 | Planned
6 | 2016-06-21 | 7 | 2016-06-27 | 0 | Planned
7 | 2016-06-28 | 7 | 2016-07-04 | 0 | Planned
8 | 2016-07-05 | 7 | 2016-07-11 | 0 | Planned
9 | 2016-07-12 | 7 | 2016-07-18 | 0 | Planned
10 | 2016-07-19 | 7 | 2016-07-25 | 0 | Planned
11 | 2016-07-26 | 7 | 2016-08-01 | 0 | Planned
12 | 2016-08-02 | 7 | 2016-08-08 | 0 | Planned
13 | 2016-08-09 | 7 | 2016-08-15 | 0 | Planned
Unplanned
Unplanned
|  |  | Unallocated stories | 0
Formulas:
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
1 | Design database | Done |  | 1
2 | UI: G100 | Done |  | 1
3 | UI: P200 | Done |  | 1
4 | UI: T300 | Done |  | 1
| UI: A400 | Done
5 | Document: User Requirement Design | Done |  | 1
6 | Document: Software Requirement Design | Done |  | 2
7 | Common: Implement Authentication functions | Done |  | 2
8 | Common: Implement CRUD for User functions | Done |  | 2
9 | Child Profile: Implement creation/edition functions | Done |  | 3
10 | Child Profile: Implement information management | Done |  | 3
11 | Immunization: Standard Immunization System Manegement | Done |  | 3
12 | Immunization: Child Profile's Immunization Schedule Detail Management | Done |  | 4
13 | Immunization: Immunization Schedule Notification | Done |  | 4
14 | Immunization: Immunization Schedule Detail | Done |  | 5
15 | Nutrition Suggestion: Child Standard Nutritional System Management | Done |  | 5
16 | Nutrition Suggestion: Child Nutrition Detail Management | Done |  | 6
17 | Nutrition Suggestion: Nutrition Suggestion Notification | Done |  | 7
18 | Visual Concern: Camera & Streaming Configuration. | Done |  | 7
19 | Visual Concern: Online Streaming Video From Camera | Done |  | 8
20 | Report: Report Creation | Done |  | 9
21 | Report: Report Detail | Done |  | 9
22 | Teaching Scheduler: Teaching Scheduler Management | Done |  | 10
23 | Teaching Scheduler: Teaching Schedule Detail | Done |  | 10
Sort Product Backlog
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 137 |  | Sprint count | 5
Count trend from last |  |  | 3 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 30 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 |  |  | 25 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 25 |  | Trend count | 7 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 25 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 25 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 25 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 3
Original estimate - Avg |  |  | 5
Original estimate - Max |  |  | 8 |  | Standard Dev. | 2.8284
3 |  |  | 6
Realized average |  |  | 6 |  | LastPlanned | 28
Average last 8 |  |  | 6 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 6
Trend |  |  | 6
Realized + St. Dev |  |  | 6
Realized - St. Dev |  |  | 6
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 137 | 23 | 23 | 137 | 137 | 137 | 0 | 0 | 137 | 137.6667 | 137.6667 | 0 | 25 | 25 | 25
2 | 114 | 29 | 27 | 137 | 114 | 114 | 0 | 0 | 114 | 112.6667 | 112.6667 | 0 | 25 | 25 | 25
3 | 87 | 31 |  | 137 | 87 | 87 | 0 | 0 | 87 | 87.6667 | 87.6667 | 0 | 25 | 25 | 25
4 | 56 | 28 |  | 137 | 0 | 0 | 56 | 56 | 56 | 62.6667 | 62.6667 | 0 | 25 | 25 | 25
5 | 28 | 28 |  | 137 | 0 | 0 | 28 | 28 | 28 | 37.6667 | 37.6667 | 0 | 25 | 25 | 25
6 | [9 empty] | 12.6667 | 12.6667 | 0 | 25 | 25 | 25
7 | [9 empty] | 0 | 0 | 0 | 25 | 25 | 25
8 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
9 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
10 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
11 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
12 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
13 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
14 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
15 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
16 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
17 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
18 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
19 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
20 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
21 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
22 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
23 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
24 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1 1705-2405
1
17/05/2016 - 24/05/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 92 | 5 | 8 | 7 | 11 | 11 | 8 | 7
Task rows | 17 | Done days | 7 |  | 92 | 78.8571 | 65.7143 | 52.5714 | 39.4286 | 26.2857 | 13.1429
Warning! These are necessary |  | Trend |  |  | 10 | 9.7 | 9.4 | 9.1 | 8.8 | 8.5 | 8.2 | 7.9 | 7.6 | 7.3 | 7 | 6.7 | 6.4 | 6.1 | 5.8 | 5.5 | 5.2 | 4.9 | 4.6 | 4.3 | 4 | 3.7 | 3.4 | 3.1 | 2.8
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
UI: Home page - G101 | 2 | NghiaDH | Done | 2 | 2: 2
UI: Login - G103 | 2 | NghiaDH | Done | 1 | bar: 2
UI: Home page for Parent - P201 | 2 | NghiaDH | Done | 2 | 3: 2
UI: Home page for Teacher - T301 | 2 | NghiaDH | Done | 2 | 3: 2
UI: Home page for Admin - A401 | 3 | NghiaDH | Done | 5 | 4: 2; 5: 1
UI: Child profile detail first design - P214 | 2 | NghiaDH | Done | 3
UI: Admin user management (common) | 3 | NghiaDH | Done | 3
UI: Admin childprofile management (common) | 3 | NghiaDH | Done | 5
ERD |  | AnhND | Done | 8 | 1: 2; 2: 2
Overview UseCase |  | ThanhLD | Done | 5 | 1: 2
Class Diagram |  | NghiaDH | Done | 5
Database design | 1 | ThanhLD | Done | 9 | 4: 2; 5: 3; 6: 2; 7: 2
System Architect Design |  | ThanhLD | Done | 8 | 4: 2; 5: 2; 6: 2; 7: 2
Build Project Source Code Structure Basic Element (Front, Back) |  | ThanhLD | Done | 10
Research: Immunization for child lower 5 yearolds | 5 | AnhND | Done | 8 | 1: 1; 2: 2; 3: 1; 4: 2; 5: 2
Research: Nutrition for child lower 5 yearolds | 5 | AnhND | Done | 8 | 2: 1; 3: 1; 4: 1; 5: 1; 6: 2; 7: 2
Research: IP camera and streaming server |  | ThanhLD | Done | 8 | 3: 1; 4: 2; 5: 2; 6: 2; 7: 1
|  |  |  | 92 | 1: 92
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2 2405-3105
2
24/05/2016 - 31/05/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 42 | 4 | 9 | 8 | 6 | 2
Task rows | 13 | Done days | 5 |  | 42 | 36 | 30 | 24 | 18 | 12 | 6
Warning! These are necessary |  | Trend |  |  | 7.2 | 6.5 | 5.8 | 5.1 | 4.4 | 3.7 | 3 | 2.3 | 1.6 | 0.9 | 0.2
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 7.2 1: 1; 6.5 2: 2; 5.8 3: 3; 5.1 4: 4; 4.4 5: 5; 3.7 6: 6; 3 7: 7
UI: Home page - G101 | 2 | NghiaDH | Done | 2 | 6.5 2: 2
UI: Login - G103 | 2 | NghiaDH | Done | 1 | bar: 6.5 2
UI: Home page for Parent - P201 | 2 | NghiaDH | Done | 2 | 5.8 3: 2
UI: Home page for Teacher - T301 | 2 | NghiaDH | Done | 2 | 5.8 3: 2
UI: Home page for Admin - A401 | 3 | NghiaDH | Done | 5 | 5.1 4: 2; 4.4 5: 1
UI: Child profile detail first design - P214 | 2 | NghiaDH | Done | 3
UI: Admin user management (common) | 3 | NghiaDH | Done | 3
UI: Admin childprofile management (common) | 3 | NghiaDH | Done | 5
UI: Child Profile List - P211 | 2 | NghiaDH | Done | 3 | 7.2 1: 2; 6.5 2: 1
UI: Create Child Profile - P212 | 2 | NghiaDH | Done | 5 | 6.5 2: 2; 5.8 3: 2; 5.1 4: 1
UI: Update Child Profile - P213 | 2 | NghiaDH | Done | 5 | 6.5 2: 2; 5.8 3: 2; 5.1 4: 1
UI: Nutrition Suggestion List - P241 | 4 | AnhND | Done | 3 | 7.2 1: 2; 6.5 2: 1
UI: Report list - T261 | 5 | NghiaDH | Done | 3 | 5.1 4: 2; 4.4 5: 1
UI: Create report - T263 | 5 | NghiaDH | Done | 5 | 4.4 5: 2; 3.7 6: 2; 3 7: 1
Integrate current UI to project source code. |  | ThanhLD | Done | 8 | 7.2 1: 3; 6.5 2: 3; 5.8 3: 2
API: Acoount CRUD Implement |  | ThanhLD | Done | 5 | 5.1 4: 3; 4.4 5: 2
API: Child Profile CRUD Implement |  | ThanhLD | Done | 8 | 4.4 5: 3; 3.7 6: 3; 3 7: 2
API: Immunization CRUD Implement |  | ThanhLD | Done | 5 | 3.7 6: 3; 3 7: 2
API: Nutrition CRUD Implement |  | AnhND | Done | 5 | 3.7 6: 3; 3 7: 2
Research: Camera Streaming Video To Server |  | ThanhLD | Done | 8 | 7.2 1: 5; 6.5 2: 2; 5.8 3: 1
Research: Suitable camera for this project |  | ThanhLD | Done | 8 | 4.4 5: 3; 3.7 6: 2; 3 7: 3
|  |  |  | 71 | 7.2 1: 71
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3 3105-0706
3
31/05/2016 - 07/06/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 83 | 9 | 9 | 11 | 13 | 17 | 13 | 10
Task rows | 20 | Done days | 7 |  | 83 | 71.1429 | 59.2857 | 47.4286 | 35.5714 | 23.7143 | 11.8571
Warning! These are necessary |  | Trend |  |  | 13.6 | 13.4 | 13.2 | 13 | 12.8 | 12.6 | 12.4 | 12.2 | 12 | 11.8 | 11.6 | 11.4 | 11.2 | 11 | 10.8 | 10.6 | 10.4 | 10.2 | 10 | 9.8 | 9.6 | 9.4 | 9.2 | 9 | 8.8
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
UI: Login |  | NghiaDH | Done | 1 | bar: 1
UI: Admin List of parent |  | NghiaDH | Done | 3 | bar: 2 to 4
UI: Admin create new Parent |  | NghiaDH | Done | 4 | 3: 2; 4: 1; 5: 1
UI: Admin List of teacher |  | NghiaDH | Done | 2 | bar: 4 to 5
UI: Admin create new Teacher |  | NghiaDH | Done | 3 | 5: 2; 6: 1
UI: Admin List of class |  | AnhND | Done | 3 | 1: 2; 2: 1
UI: Admin create new Class |  | AnhND | Done | 2 | bar: 1 to 2
UI: Admin assign Teacher and child to class. |  | AnhND | Done | 2 | 2: 2
Integrate current UI of Parent with API |  | ThanhLD | Done | 10 | 3: 2; 4: 2; 5: 2; 6: 2; 7: 2
Integrate current UI of Teacher with API |  | ThanhLD | Done | 10 | 3: 2; 4: 2; 5: 2; 6: 2; 7: 2
API: Authenticatetion |  | ThanhLD | Done | 6 | 1: 5
API: Account List by role |  | ThanhLD | Done | 2 | 3: 2
API: Class CRUD |  | AnhND | Done | 3 | 6: 2; 7: 1
API: Assign teacher to class |  | AnhND | Done | 2 | 2: 2
API: Assign child to class |  | AnhND | Done | 2 | 2: 2
API: HealthRate CRUD |  | AnhND | Done | 3 | 3: 2; 4: 1
API: Create/Update child health |  | AnhND | Done | 2 | bar: 4 to 5
API: Report CRUD |  | AnhND | Done | 3 | bar: 4 to 6
Stream video from IP Camera to Server. |  | ThanhLD | Done | 10 | 4: 3; 5: 3; 6: 2; 7: 2
Play stream video on player in UI. |  | ThanhLD | Done | 10 | 5: 4; 6: 3; 7: 3
83
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp4 0706-1406
4
07/06/2016 - 14/06/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 100 | 15 | 20 | 19 | 15 | 7 | 9 | 14
Task rows | 27 | Done days | 7 |  | 100 | 85.7143 | 71.4286 | 57.1429 | 42.8571 | 28.5714 | 14.2857
Warning! These are necessary |  | Trend |  |  | 19.2 | 17.6 | 16 | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
UI: P231 |  | NghiaDH | Done | 3 | 1: 2; 2: 1
UI: P232 |  | NghiaDH | Done | 2 | 2: 2
UI: P233 |  | NghiaDH | Done | 3 | 3: 3
UI: P241 |  | NghiaDH | Done | 2 | 1: 2
UI: P242 |  | NghiaDH | Done | 2 | 2: 2
UI: A441 |  | NghiaDH | Done | 1 | bar: 1
UI: A451 |  | ThanhLD | Done | 2 | 1: 2
UI: A471 |  | ThanhLD | Done | 2 | 2: 2
UI: A472 |  | ThanhLD | Done | 2 | 3: 2
UI: A481 |  | ThanhLD | Done | 3 | 3: 2; 4: 1
UI: A482 |  | ThanhLD | Done | 2 | 4: 2
Integrate current UI of Parent with API |  | NghiaDH | Ongoing | 6 | 4: 3; 5: 2; 6: 1
Integrate current UI of Admin with API |  | ThanhLD | Done | 8 | 3: 4; 4: 3; 5: 1
API: Immunization List (Child/ standard) |  | NghiaDH | Done | 5 | 1: 2; 2: 2; 3: 1
API: Immunization Detail (Child/ standard) |  | NghiaDH | Done | 3 | 2: 2; 3: 1
API: Create Nutrition suggestion for child |  | ThanhLD | Done | 5 | 1: 3; 2: 2
API: Check attendence |  | ThanhLD | Done | 4 | 2: 2; 3: 2
API: Check child health |  | ThanhLD | Done | 5 | 4: 3; 5: 1
API: List teaching schedule |  | AnhND | Done | 3 | 1: 3
API: create teaching schedule |  | AnhND | Done | 2 | 2: 2
API: Post CRUD |  | ThanhLD | Done | 3 | 3: 2; 4: 1
Research: Stored video when streaming. |  | ThanhLD | Done | 5 | 2: 1; 3: 1; 4: 1; 5: 2
Research: Stored video when streaming. |  | NghiaDH | Done | 5 | 2: 2; 3: 1; 4: 1; 5: 1
System integration. Preparing Alpha version for releasing. |  | ThanhLD | Ongoing | 15 | 6: 8; 7: 7
Guest and Parent function test |  | NghiaDH | Ongoing | 3 | 7: 3
Admin and Teacher functions test |  | AnhND | Ongoing | 3 | 7: 3
System test. |  | ThanhLD | Ongoing | 1 | bar: 7
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp5 1406-2806
5
14/06/2016 -21/06/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 184 | 23 | 29 | 27 | 22 | 7 |  | 1
Task rows | 12 | Done days | 6 |  | 184 | 157.7143 | 131.4286 | 105.1429 | 78.8571 | 52.5714 | 26.2857
Warning! These are necessary |  | Trend |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Integrate current UI of Parent with API |  | NghiaDH | Done | 15 | 1: 5; 2: 3; 3: 2
Integrate current UI of Teacher with API |  | AnhND | Planned | 15 | 1: 5; 2: 3
Integrate current UI of Home page with API |  | ThanhLD | Ongoing | 6 | 1: 3; 2: 3
Integrate current UI of ChildProfile with API |  | ThanhLD | Done | 8 | 1: 5; 2: 3
Media management in admin |  | ThanhLD | Planned | 5 | 2: 3; 3: 2
API: Dashboard Information |  | NghiaDH | Planned | 5 | 3: 3; 4: 2
Improve UI for Parent UI |  | NghiaDH | Done | 40 | 2: 2; 3: 5; 4: 5
Improve UI for Teacher UI |  | AnhND | Done | 40 | 2: 2; 3: 5; 4: 5
Improve UI for Admin UI |  | ThanhLD | Done | 12 | 2: 5; 3: 5; 4: 5
Fix bug website |  | Team | Done | 30 | 1: 5; 2: 5; 3: 5; 4: 5
Demo: Stored video when streaming. |  | ThanhLD | Ongoing | 5 | 5: 4; 7: 1
Design mobile structure |  | ThanhLD | Planned | 3 | 5: 3
184
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp6 2806-0507
6
28/06/2016 -05/07/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 190 | 0
Task rows | 14 | Done days | 1 |  | 190 | 162.8571 | 135.7143 | 108.5714 | 81.4286 | 54.2857 | 27.1429
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Integrate current UI of Teacher with API |  | AnhND | Planned | 14
Create usecase specifications for teacher |  | AnhND | Planned | 8
Create usecase specifications for teacher |  | NghiaDH | Planned | 8
Improve report of child content |  | ThanhLD | Planned | 20
Improve teacher page (create report) |  | ThanhLD | Planned | 20
Improve Calendar for Immunization |  | ThanhLD | Planned | 16
Media management in admin |  | ThanhLD | Planned | 8
API: Dashboard Information |  | NghiaDH | Planned | 8
System integration. Preparing Alpha version for releasing. |  | ThanhLD | Planned | 24
Guest and Parent function test |  | NghiaDH | Planned | 8
Admin and Teacher functions test |  | AnhND | Planned | 8
System test. |  | ThanhLD | Planned | 8
Design mobile structure |  | ThanhLD | Planned | 16
Build mobile structure |  | ThanhLD | Planned | 24
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp7 0507-1207
7
09/03/2016 -15/03/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 13 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Teacher screen - Child immunization |  | NghiaDH | Done
Teacher screen - Current class |  | NghiaDH | Done
Teacher screen - Nutrition |  | NghiaDH | Done
Teacher screen - Teaching schedule |  | NghiaDH | Done
Teacher screen - report |  | NghiaDH | Done
Teacher screen - attendence |  | NghiaDH | Ongoing
Parent screen - view detail report |  | AnhND | Done
Admin screen - Menu management |  | AnhND | Done
Mobile - UI design |  | ThanhLD | Done
API Mobile - login API |  | ThanhLD | Done
API Mobile - recover password |  | ThanhLD | Done
KhuongND vắng ko lý do, ko tập trung làm việc, ảnh hưởng đến nhóm (đang xem xét có nên tiếp tục ko)
CuongHH xong các task trước t3 (ko thì ở nhà)
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp8 1207-1907
8
16/03/2016 -22/03/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 23 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Teacher screen - attendance screen |  | NghiaDH | Done
Teacher screen - attendance notify API |  | NghiaDH | Ongoing
Teacher screen - child health check |  | NghiaDH | Done
Teacher screen - child attendance |  | NghiaDH | Done
Teacher screen/Parent screen - child report detail |  | NghiaDH | Done
Teacher/Parent - comment on child report |  | AnhND | Done
Teacher screen - Teacher menu after login |  | ThanhLD | Done
Teacher screen - System auto render childHealth and ChildImmunization |  | NghiaDH | Done
Parent screen - Report list |  | AnhND | Done
Parent screen - Report detail |  | AnhND | Done
Parent screen - child profile detail - immunization |  | AnhND | Done
Parent screen - child profile detail - class attendance |  | AnhND | Done
Parent screen - child profile detail - nutrition suggestion |  | AnhND | Done
Mobile - home screen general |  | ThanhLD | Done
Intergate Mobile API - home screen general |  | ThanhLD | Done
Mobile - user profile screen |  | ThanhLD | Done
Intergate Mobile API - user profile screen |  | ThanhLD | Done
Design - menu of parent app and menu of teacher app |  | ThanhLD | Done
Member nên tranh thủ Time hoàn thành task của mình
Member nên chuẩn bị list todo và list QA để khi thảo luận không bị lang mang và miss
Team lead nên bám sát task theo hằng ngày bằng cách hỏi checklist của từng member
Lead hướng dãn làm checklist cho member
Member nên tự design theo ý mình rùi sau đó confirm lại team
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp9 1907-2607
9
23/03/2016 -29/03/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 16 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Feature: Notify on web |  | ThanhLD | Planned
Feature: Attendance notify (web) - from teacher to parent |  | NghiaDH | Planned
Feature: Input child immunization by teacher/parent |  | NghiaDH | Planned
Feature: Immunization notification (web) to teacher and parent |  | AnhND | Planned
System integration in website. |  | NghiaDH | Done
System test. |  | AnhND | Done
Mobile - Parent: child profile list |  | ThanhLD | Planned
Mobile - Parent: child profile create |  | ThanhLD | Planned
Mobile - Parent: child profile detail |  | ThanhLD | Planned
Mobile - Parent: child report list |  | ThanhLD | Planned
Mobile - Parent: child report detail |  | ThanhLD | Planned
Mobile - Parent: View video camera |  | ThanhLD | Planned
Mobile - Teacher: Leftmenu |  | ThanhLD | Planned
Nghĩa rất cố gắng để hoàn thiện các chức năng đang dang dỡ. Tích hợp các chức năng với nhau.
Duy Anh code hơi chậm, nhưng cũng rất cố gắng. Nên làm nhiều và học hỏi thêm mọi người.
Thanh code mobile còn chậm, khó khăn gặp phải ở cách hiển thị trên mobile.
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp10 2607-0208
10
30/03/2016 -05/04/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 8 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Mobile: sort & filter
Mobile: search flight
API: search & show flight detail
API: filter flight
Search algorithm: ranking by user behaviors |  | TrucGS | Done
Adjust search UI |  | CuongHH | Done
Adjust detail UI |  | CuongHH | Done
Adjust admin dashboard |  | KhuongND | Done
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sprint Sheet Template
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Task Slips
Story ID: | 1 | Story: | This is a sample story
Task: | Example task
#REF!
Initial Estimate | 5 | Work Done |  | Work Left
Story ID: | 1 | Story: | This is a sample story
Task: | Example task 2
Responsible Person: NghiaDH
Initial Estimate | 7 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | Example task 3
Responsible Person: NghiaDH
Initial Estimate | 12 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | <Delete these example lines>
Responsible Person: NghiaDH
Initial Estimate | 9 | Work Done |  | Work Left