## Release Plan
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2016-09-07 | 7 | 2016-09-13 | 0 | Planned |  | Requirement & Design (DB, UI, UX)
2 | 2016-09-14 | 7 | 2016-09-20 | 0 | Planned
3 | 2016-09-21 | 7 | 2016-09-27 | 0 | Planned |  | Prototype
4 | 2016-09-28 | 7 | 2016-10-04 | 0 | Planned
5 | 2016-10-05 | 7 | 2016-10-11 | 0 | Planned
6 | 2016-10-12 | 7 | 2016-10-18 | 0 | Planned |  | Basic Feature App
7 | 2016-10-19 | 7 | 2016-10-25 | 0 | Planned
8 | 2016-10-26 | 7 | 2016-11-01 | 0 | Planned |  | Advanced Feature App
9 | 2016-11-02 | 7 | 2016-11-08 | 0 | Planned |  | Report 2 SPM
10 | 2016-11-09 | 7 | 2016-11-15 | 0 | Planned |  | Report 3 SRS
11 | 2016-11-16 | 7 | 2016-11-22 | 0 | Planned |  | Report 4 SDD
12 | 2016-11-23 | 7 | 2016-11-29 | 0 | Planned |  | Report 5
13 | 2016-11-30 | 7 | 2016-12-06 | 0 | Planned |  | Report 6 User Manual
Unplanned
Unplanned
|  |  | Unallocated stories | 0
Formulas:
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
100 | Authentication | Planned |  | 1
101 | Login | Planned |  | 1
102 | Register | Planned |  | 1
200 | Teacher | Planned |  | 1
201 | Create Course | Planned
202 | View Course | Planned |  | 1
203 | Edit Course | Planned |  | 2
204 | Delete Course | Planned |  | 2
205 | Open Course | Planned
206 | Close Course | Planned
207 | View Enrolled Learner | Planned
208 | View Learner Rank | Planned
209 | Create Time Frame | Planned
210 | View Time Frame | Planned
211 | Edit Time Frame | Planned
212 | Delete Time Frame | Planned
213 | Manage Chapter | Planned
214 | Manage Lesson | Planned
215 | Withdraw Money | Planned
300 | Learner | Planned |  | 2
301 | Search Teacher | Planned |  | 3
302 | Search Course | Planned |  | 3
303 | View Enrolled Course | Planned |  | 3
304 | View Course Detail | Planned |  | 4
305 | Enroll Course | Planned |  | 5
306 | Vote Course | Planned |  | 5
307 | View Teacher's Time Frame | Planned |  | 6
308 | Follow Teacher | Planned |  | 7
309 | View Course Report | Planned |  | 7
310 | Deposit Money | Planned
400 | Authenticated User | Planned |  | 9
401 | View Registered Slot | Planned |  | 9
402 | Cancel Registration | Planned |  | 10
403 | Login to Meeting | Planned
404 | Cancel Meeting | Planned
405 | View Profile | Planned
406 | Edit Profile | Planned
407 | Use Support Tool | Planned
Sort Product Backlog
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 137 |  | Sprint count | 5
Count trend from last |  |  | 3 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 30 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 |  |  | 25 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 25 |  | Trend count | 7 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 25 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 25 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 25 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 3
Original estimate - Avg |  |  | 5
Original estimate - Max |  |  | 8 |  | Standard Dev. | 2.8284
3 |  |  | 6
Realized average |  |  | 6 |  | LastPlanned | 28
Average last 8 |  |  | 6 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 6
Trend |  |  | 6
Realized + St. Dev |  |  | 6
Realized - St. Dev |  |  | 6
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 137 | 23 | 23 | 137 | 137 | 137 | 0 | 0 | 137 | 137.6667 | 137.6667 | 0 | 25 | 25 | 25
2 | 114 | 29 | 27 | 137 | 114 | 114 | 0 | 0 | 114 | 112.6667 | 112.6667 | 0 | 25 | 25 | 25
3 | 87 | 31 |  | 137 | 87 | 87 | 0 | 0 | 87 | 87.6667 | 87.6667 | 0 | 25 | 25 | 25
4 | 56 | 28 |  | 137 | 0 | 0 | 56 | 56 | 56 | 62.6667 | 62.6667 | 0 | 25 | 25 | 25
5 | 28 | 28 |  | 137 | 0 | 0 | 28 | 28 | 28 | 37.6667 | 37.6667 | 0 | 25 | 25 | 25
6 | [9 empty] | 12.6667 | 12.6667 | 0 | 25 | 25 | 25
7 | [9 empty] | 0 | 0 | 0 | 25 | 25 | 25
8 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
9 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
10 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
11 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
12 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
13 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
14 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
15 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
16 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
17 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
18 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
19 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
20 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
21 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
22 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
23 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
24 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
2016-09-07
2016-09-13
Sprint implementation days | 7 |  |  | Effort (hour) |  | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 36 | 20 | 4 | 5 | 4 | 2 | 1
Task rows | 10 | Done days | 5 |  |  | 36 | 30.8571 | 25.7143 | 20.5714 | 15.4286 | 10.2857 | 5.1429
Warning! These are necessary |  | Trend |  |  |  | 5 | 4.1 | 3.2 | 2.3 | 1.4 | 0.5
template rows |  | Trend Days | 5 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | Remain | 5 1: 1; 4.1 2: 2; 3.2 3: 3; 2.3 4: 4; 1.4 5: 5; 0.5 6: 6; 0.5 7: 7
Design ERD |  | HungVK | Planned | 2 | 0 | 4.1 2: 2
Design Overview Usecase |  | DuyNC | Planned | 1 | 0 | bar: 4.1 2
Design Physical database |  | HungVK | Planned | 2 | 0 | 3.2 3: 2
Design Class diagram |  | HungVK | Planned | 2 | 0 | 3.2 3: 2
Report 1: Introduction |  | PhucTQ | Planned | 5 | 2 | 2.3 4: 2; 1.4 5: 1
UI: Login Page |  | ThanhNP | Planned | 3 | 3
UI: Register Page |  | ThanhNP | Planned | 3 | 3
UI: Home Page |  | ThanhNP | Planned | 5 | 5
UI: Search Page |  | ThanhNP | Planned | 8 | 4 | 5 1: 2; 4.1 2: 2
UI: Search Result Page |  | ThanhNP | Planned | 5 | 3 | 5 1: 2
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
2
2016-09-14
2016-09-20
Sprint implementation days | 7 |  |  | Effort (hour) |  | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 12 | 0 | 0 | 3 | 4 | 2 | 1
Task rows | 5 | Done days | 4 |  |  | 12 | 10.2857 | 8.5714 | 6.8571 | 5.1429 | 3.4286 | 1.7143
Warning! These are necessary |  | Trend |  |  |  | 1.2 | 1.9 | 2.6 | 3.3 | 4 | 4.7 | 5.4 | 6.1 | 6.8 | 7.5 | 8.2 | 8.9 | 9.6 | 10.3 | 11 | 11.7 | 12.4 | 13.1 | 13.8 | 14.5 | 15.2 | 15.9 | 16.6 | 17.3 | 18
template rows |  | Trend Days | 4 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | Remain | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Bom: Register API | 2 | PhucTQ | Done | 2 | 0 | 2: 2
Mockup: Register | 2 | PhucTQ | Done | 1 | 0 | bar: 2
Bom: Login API | 1 | PhucTQ | Done | 2 | 0 | 3: 2
App: Login in | 1 | PhucTQ | Done | 2 | 0 | 3: 2
App: Login using Facebook | 1 | DuyNC | Done | 5 | 0 | 4: 2; 5: 1
Bom: Create Course API | 7 | PhucTQ | Done | 3 | 0
Bom: Teacher View Course API | 8 | PhucTQ | Done | 3 | 0
Bom: Create TimeFrame API | 3 |  | Done | 5 | 0
Bom: Teacher View TimeFrame API | 4 |  | Done | 3 | 0 | 1: 2; 2: 1
App: Create Course | 7 | PhucTQ | Done | 5 | 0 | 2: 2; 3: 2; 4: 1
App: Teacher View Course | 8 | PhucTQ | Done | 5 | 0 | 2: 2; 3: 2; 4: 1
App: Create TimeFrame | 3 |  | Done | 3 | 0 | 1: 2; 2: 1
App: Teacher View TimeFrame | 4 |  | Done | 3 | 0 | 4: 2; 5: 1
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
3
2016-09-21
2016-09-27
Sprint implementation days | 7 |  |  | Effort (hour) |  | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 56 | 36 | 10 | 8 | 2
Task rows | 20 | Done days | 3 |  |  | 56 | 48 | 40 | 32 | 24 | 16 | 8
Warning! These are necessary |  | Trend |  |  |  | 10.6667 | 6.6667 | 2.6667
template rows |  | Trend Days | 3 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | Remain | 10.6667 1: 1; 6.6667 2: 2; 2.6667 3: 3; 2.6667 4: 4; 2.6667 5: 5; 2.6667 6: 6; 2.6667 7: 7
Doc: Design Use-case Diagram |  | PhucTQ | Done | 4 | 0 | 10.6667 1: 2; 6.6667 2: 2
Doc: Design Conceptual Data Model |  | PhucTQ | Done | 8 | 0 | 10.6667 1: 4; 6.6667 2: 3; 2.6667 3: 1
Doc: Design Logical Data Model |  | PhucTQ | Done | 8 | 0 | 10.6667 1: 4; 6.6667 2: 3; 2.6667 3: 1
Doc: Design Physical Data Model |  | PhucTQ | Planned | 4 | 4 | 10.6667 1: 0; 6.6667 2: 0
UI: Login |  | PhucTQ | Planned | 2 | 2
UI: Register |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Course |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Chapter |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Lesson |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Time Frame |  | PhucTQ | Planned | 2 | 2
UI: Teacher Create Time Slot |  | PhucTQ | Planned | 2 | 2
UI: Learner Search Teacher |  | DuyNC | Ongoing | 2 | 2
UI: Learner Search Course |  | DuyNC | Ongoing | 2 | 2
UI: Leaner View Teacher Details |  | DuyNC | Planned | 2 | 2
UI: Leaner View Course Details |  | DuyNC | Planned | 2 | 2
UI: Leaner Follow Teacher |  | DuyNC | Planned | 2 | 2
UI: Leaner Enroll Course |  | DuyNC | Planned | 2 | 2
UI: Leaner Register Time Slot |  | DuyNC | Planned | 2 | 2
UI: Teacher View Upcomming Meeting |  | DuyNC | Planned | 2 | 2
UI: Leaner View Upcomming Meeting |  | DuyNC | Planned | 2 | 2
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp4
4
07/06/2016 - 14/06/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 100 | 15 | 20 | 19 | 15 | 7 | 9 | 14
Task rows | 27 | Done days | 7 |  | 100 | 85.7143 | 71.4286 | 57.1429 | 42.8571 | 28.5714 | 14.2857
Warning! These are necessary |  | Trend |  |  | 19.2 | 17.6 | 16 | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
UI: P231 |  | NghiaDH | Done | 3 | 1: 2; 2: 1
UI: P232 |  | NghiaDH | Done | 2 | 2: 2
UI: P233 |  | NghiaDH | Done | 3 | 3: 3
UI: P241 |  | NghiaDH | Done | 2 | 1: 2
UI: P242 |  | NghiaDH | Done | 2 | 2: 2
UI: A441 |  | NghiaDH | Done | 1 | bar: 1
UI: A451 |  | ThanhLD | Done | 2 | 1: 2
UI: A471 |  | ThanhLD | Done | 2 | 2: 2
UI: A472 |  | ThanhLD | Done | 2 | 3: 2
UI: A481 |  | ThanhLD | Done | 3 | 3: 2; 4: 1
UI: A482 |  | ThanhLD | Done | 2 | 4: 2
Integrate current UI of Parent with API |  | NghiaDH | Ongoing | 6 | 4: 3; 5: 2; 6: 1
Integrate current UI of Admin with API |  | ThanhLD | Done | 8 | 3: 4; 4: 3; 5: 1
API: Immunization List (Child/ standard) |  | NghiaDH | Done | 5 | 1: 2; 2: 2; 3: 1
API: Immunization Detail (Child/ standard) |  | NghiaDH | Done | 3 | 2: 2; 3: 1
API: Create Nutrition suggestion for child |  | ThanhLD | Done | 5 | 1: 3; 2: 2
API: Check attendence |  | ThanhLD | Done | 4 | 2: 2; 3: 2
API: Check child health |  | ThanhLD | Done | 5 | 4: 3; 5: 1
API: List teaching schedule |  | AnhND | Done | 3 | 1: 3
API: create teaching schedule |  | AnhND | Done | 2 | 2: 2
API: Post CRUD |  | ThanhLD | Done | 3 | 3: 2; 4: 1
Research: Stored video when streaming. |  | ThanhLD | Done | 5 | 2: 1; 3: 1; 4: 1; 5: 2
Research: Stored video when streaming. |  | NghiaDH | Done | 5 | 2: 2; 3: 1; 4: 1; 5: 1
System integration. Preparing Alpha version for releasing. |  | ThanhLD | Ongoing | 15 | 6: 8; 7: 7
Guest and Parent function test |  | NghiaDH | Ongoing | 3 | 7: 3
Admin and Teacher functions test |  | AnhND | Ongoing | 3 | 7: 3
System test. |  | ThanhLD | Ongoing | 1 | bar: 7
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp5 1406-2806
5
14/06/2016 -21/06/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 184 | 23 | 29 | 27 | 22 | 7 |  | 1
Task rows | 12 | Done days | 6 |  | 184 | 157.7143 | 131.4286 | 105.1429 | 78.8571 | 52.5714 | 26.2857
Warning! These are necessary |  | Trend |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Integrate current UI of Parent with API |  | NghiaDH | Done | 15 | 1: 5; 2: 3; 3: 2
Integrate current UI of Teacher with API |  | AnhND | Planned | 15 | 1: 5; 2: 3
Integrate current UI of Home page with API |  | ThanhLD | Ongoing | 6 | 1: 3; 2: 3
Integrate current UI of ChildProfile with API |  | ThanhLD | Done | 8 | 1: 5; 2: 3
Media management in admin |  | ThanhLD | Planned | 5 | 2: 3; 3: 2
API: Dashboard Information |  | NghiaDH | Planned | 5 | 3: 3; 4: 2
Improve UI for Parent UI |  | NghiaDH | Done | 40 | 2: 2; 3: 5; 4: 5
Improve UI for Teacher UI |  | AnhND | Done | 40 | 2: 2; 3: 5; 4: 5
Improve UI for Admin UI |  | ThanhLD | Done | 12 | 2: 5; 3: 5; 4: 5
Fix bug website |  | Team | Done | 30 | 1: 5; 2: 5; 3: 5; 4: 5
Demo: Stored video when streaming. |  | ThanhLD | Ongoing | 5 | 5: 4; 7: 1
Design mobile structure |  | ThanhLD | Planned | 3 | 5: 3
184
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp6 2806-0507
6
28/06/2016 -05/07/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 190 | 0
Task rows | 14 | Done days | 1 |  | 190 | 162.8571 | 135.7143 | 108.5714 | 81.4286 | 54.2857 | 27.1429
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Integrate current UI of Teacher with API |  | AnhND | Planned | 14
Create usecase specifications for teacher |  | AnhND | Planned | 8
Create usecase specifications for teacher |  | NghiaDH | Planned | 8
Improve report of child content |  | ThanhLD | Planned | 20
Improve teacher page (create report) |  | ThanhLD | Planned | 20
Improve Calendar for Immunization |  | ThanhLD | Planned | 16
Media management in admin |  | ThanhLD | Planned | 8
API: Dashboard Information |  | NghiaDH | Planned | 8
System integration. Preparing Alpha version for releasing. |  | ThanhLD | Planned | 24
Guest and Parent function test |  | NghiaDH | Planned | 8
Admin and Teacher functions test |  | AnhND | Planned | 8
System test. |  | ThanhLD | Planned | 8
Design mobile structure |  | ThanhLD | Planned | 16
Build mobile structure |  | ThanhLD | Planned | 24
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp7 0507-1207
7
09/03/2016 -15/03/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 13 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Teacher screen - Child immunization |  | NghiaDH | Done
Teacher screen - Current class |  | NghiaDH | Done
Teacher screen - Nutrition |  | NghiaDH | Done
Teacher screen - Teaching schedule |  | NghiaDH | Done
Teacher screen - report |  | NghiaDH | Done
Teacher screen - attendence |  | NghiaDH | Ongoing
Parent screen - view detail report |  | AnhND | Done
Admin screen - Menu management |  | AnhND | Done
Mobile - UI design |  | ThanhLD | Done
API Mobile - login API |  | ThanhLD | Done
API Mobile - recover password |  | ThanhLD | Done
KhuongND vắng ko lý do, ko tập trung làm việc, ảnh hưởng đến nhóm (đang xem xét có nên tiếp tục ko)
CuongHH xong các task trước t3 (ko thì ở nhà)
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp8 1207-1907
8
16/03/2016 -22/03/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 23 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Teacher screen - attendance screen |  | NghiaDH | Done
Teacher screen - attendance notify API |  | NghiaDH | Ongoing
Teacher screen - child health check |  | NghiaDH | Done
Teacher screen - child attendance |  | NghiaDH | Done
Teacher screen/Parent screen - child report detail |  | NghiaDH | Done
Teacher/Parent - comment on child report |  | AnhND | Done
Teacher screen - Teacher menu after login |  | ThanhLD | Done
Teacher screen - System auto render childHealth and ChildImmunization |  | NghiaDH | Done
Parent screen - Report list |  | AnhND | Done
Parent screen - Report detail |  | AnhND | Done
Parent screen - child profile detail - immunization |  | AnhND | Done
Parent screen - child profile detail - class attendance |  | AnhND | Done
Parent screen - child profile detail - nutrition suggestion |  | AnhND | Done
Mobile - home screen general |  | ThanhLD | Done
Intergate Mobile API - home screen general |  | ThanhLD | Done
Mobile - user profile screen |  | ThanhLD | Done
Intergate Mobile API - user profile screen |  | ThanhLD | Done
Design - menu of parent app and menu of teacher app |  | ThanhLD | Done
Member nên tranh thủ Time hoàn thành task của mình
Member nên chuẩn bị list todo và list QA để khi thảo luận không bị lang mang và miss
Team lead nên bám sát task theo hằng ngày bằng cách hỏi checklist của từng member
Lead hướng dãn làm checklist cho member
Member nên tự design theo ý mình rùi sau đó confirm lại team
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp9 1907-2607
9
23/03/2016 -29/03/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 16 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Feature: Notify on web |  | ThanhLD | Planned
Feature: Attendance notify (web) - from teacher to parent |  | NghiaDH | Planned
Feature: Input child immunization by teacher/parent |  | NghiaDH | Planned
Feature: Immunization notification (web) to teacher and parent |  | AnhND | Planned
System integration in website. |  | NghiaDH | Done
System test. |  | AnhND | Done
Mobile - Parent: child profile list |  | ThanhLD | Planned
Mobile - Parent: child profile create |  | ThanhLD | Planned
Mobile - Parent: child profile detail |  | ThanhLD | Planned
Mobile - Parent: child report list |  | ThanhLD | Planned
Mobile - Parent: child report detail |  | ThanhLD | Planned
Mobile - Parent: View video camera |  | ThanhLD | Planned
Mobile - Teacher: Leftmenu |  | ThanhLD | Planned
Nghĩa rất cố gắng để hoàn thiện các chức năng đang dang dỡ. Tích hợp các chức năng với nhau.
Duy Anh code hơi chậm, nhưng cũng rất cố gắng. Nên làm nhiều và học hỏi thêm mọi người.
Thanh code mobile còn chậm, khó khăn gặp phải ở cách hiển thị trên mobile.
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp10 2607-0208
10
30/03/2016 -05/04/2016
Sprint implementation days | 7 |  |  | Effort (hour) | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 8 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7
Mobile: sort & filter
Mobile: search flight
API: search & show flight detail
API: filter flight
Search algorithm: ranking by user behaviors |  | TrucGS | Done
Adjust search UI |  | CuongHH | Done
Adjust detail UI |  | CuongHH | Done
Adjust admin dashboard |  | KhuongND | Done
Sort Sprint Tasks
Update Task Slips
Note on A8: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sprint Sheet Template
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Task Slips
Story ID: | 1 | Story: | This is a sample story
Task: | Example task
#REF!
Initial Estimate | 5 | Work Done |  | Work Left
Story ID: | 1 | Story: | This is a sample story
Task: | Example task 2
Responsible Person: HungVK
Initial Estimate | 7 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | Example task 3
Responsible Person: DuyNC
Initial Estimate | 12 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | <Delete these example lines>
Responsible Person: HungVK
Initial Estimate | 9 | Work Done |  | Work Left